## PROJECT PLAN #1
WORK PLAN (PROJECT PLAN) Objective: Getting good Performance metrics in Thesis progress | time axis 2024-03-11 to 2024-05-27
Category | Action item/Deliverables | Owner | Start Date | End Date | Status
Pretrained Model | Understand the the pre-trained Model | Me | 2024-03-12 | 2024-03-19 | Done | 2024-03-12: Done; 2024-03-13: Done; 2024-03-14: Done; 2024-03-15: Done; 2024-03-16: Done; 2024-03-17: Done; 2024-03-18: Done; 2024-03-19: Done
Training Pretrained Model | Train the the pre-trained Model | Me | 2024-03-19 | 2024-03-20 | Done | 2024-03-19: Done; 2024-03-20: Done
Testing Pretrained Model | Train the the pre-trained Model in Other Datasets | Me | 2024-03-20 | 2024-03-21 | Done | 2024-03-20: Done; 2024-03-21: Done
Model Developement | Make Changes to the pre-trained Models | Me | 2024-03-21 | 2024-03-29 | In Progress | 2024-03-21: In Progress; 2024-03-22: In Progress; 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress
Model Developement | Integrate the pre-trained model with my Model | Me | 2024-03-29 | 2024-04-01 | Not started | 2024-03-29: Not started; 2024-03-30: Not started; 2024-03-31: Not started; 2024-04-01: Not started
Training Model | Train the New Model | Me | 2024-04-01 | 2024-04-03 | Not started | 2024-04-01: Not started; 2024-04-02: Not started; 2024-04-03: Not started
Testing Model | Train the New Model | Me | 2024-04-04 | 2024-04-06 | Not started | 2024-04-04: Not started; 2024-04-05: Not started; 2024-04-06: Not started
Model Optimization | Hyper parameter Tuning | Me | 2024-04-07 | 2024-04-13 | Not started | 2024-04-07: Not started; 2024-04-08: Not started; 2024-04-09: Not started; 2024-04-10: Not started; 2024-04-11: Not started; 2024-04-12: Not started; 2024-04-13: Not started
Re-Training Model | Retrain the New Model | Me | 2024-04-15 | 2024-04-18 | Not started | 2024-04-15: Not started; 2024-04-16: Not started; 2024-04-17: Not started; 2024-04-18: Not started
Retesting Model | Retesting the New Model | Me | 2024-04-19 | 2024-04-23 | Not started | 2024-04-19: Not started; 2024-04-20: Not started; 2024-04-21: Not started; 2024-04-22: Not started; 2024-04-23: Not started
Documentation | Prepare Documentation | Me | 2024-04-24 | 2024-05-07 | In Progress | 2024-04-24: In Progress; 2024-04-25: In Progress; 2024-04-26: In Progress; 2024-04-27: In Progress; 2024-04-28: In Progress; 2024-04-29: In Progress; 2024-04-30: In Progress; 2024-05-01: In Progress; 2024-05-02: In Progress; 2024-05-03: In Progress; 2024-05-04: In Progress; 2024-05-05: In Progress; 2024-05-06: In Progress; 2024-05-07: In Progress

## PROJECT PLAN #2
WORK PLAN (PROJECT PLAN) Objective: Complete AICE activities, tests and milestones before respective deadlines | time axis 2024-03-01 to 2024-05-27
Category | Action item/Deliverables | Owner | Start Date | End Date | Status
Simulation | Completing all the Milestones and Tests | Me | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-01: In Progress; 2024-03-02: In Progress; 2024-03-03: In Progress; 2024-03-04: In Progress; 2024-03-05: In Progress; 2024-03-06: In Progress; 2024-03-07: In Progress; 2024-03-08: In Progress; 2024-03-09: In Progress; 2024-03-10: In Progress; 2024-03-11: In Progress; 2024-03-12: In Progress; 2024-03-13: In Progress; 2024-03-14: In Progress; 2024-03-15: In Progress; 2024-03-16: In Progress; 2024-03-17: In Progress; 2024-03-18: In Progress; 2024-03-19: In Progress; 2024-03-20: In Progress; 2024-03-21: In Progress; 2024-03-22: In Progress; 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress
Simulation | Update VacAI project board | Me | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-01: In Progress; 2024-03-02: In Progress; 2024-03-03: In Progress; 2024-03-04: In Progress; 2024-03-05: In Progress; 2024-03-06: In Progress; 2024-03-07: In Progress; 2024-03-08: In Progress; 2024-03-09: In Progress; 2024-03-10: In Progress; 2024-03-11: In Progress; 2024-03-12: In Progress; 2024-03-13: In Progress; 2024-03-14: In Progress; 2024-03-15: In Progress; 2024-03-16: In Progress; 2024-03-17: In Progress; 2024-03-18: In Progress; 2024-03-19: In Progress; 2024-03-20: In Progress; 2024-03-21: In Progress; 2024-03-22: In Progress; 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress
Spaces | Identify my city hub | Me | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-01: In Progress; 2024-03-02: In Progress; 2024-03-03: In Progress; 2024-03-04: In Progress; 2024-03-05: In Progress; 2024-03-06: In Progress; 2024-03-07: In Progress; 2024-03-08: In Progress; 2024-03-09: In Progress; 2024-03-10: In Progress; 2024-03-11: In Progress; 2024-03-12: In Progress; 2024-03-13: In Progress; 2024-03-14: In Progress; 2024-03-15: In Progress; 2024-03-16: In Progress; 2024-03-17: In Progress; 2024-03-18: In Progress; 2024-03-19: In Progress; 2024-03-20: In Progress; 2024-03-21: In Progress; 2024-03-22: In Progress; 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress
Planning | Research on solutions to VacAI | Me | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-01: In Progress; 2024-03-02: In Progress; 2024-03-03: In Progress; 2024-03-04: In Progress; 2024-03-05: In Progress; 2024-03-06: In Progress; 2024-03-07: In Progress; 2024-03-08: In Progress; 2024-03-09: In Progress; 2024-03-10: In Progress; 2024-03-11: In Progress; 2024-03-12: In Progress; 2024-03-13: In Progress; 2024-03-14: In Progress; 2024-03-15: In Progress; 2024-03-16: In Progress; 2024-03-17: In Progress; 2024-03-18: In Progress; 2024-03-19: In Progress; 2024-03-20: In Progress; 2024-03-21: In Progress; 2024-03-22: In Progress; 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress
Personal | Complete work project ahead of time | Me | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-01: In Progress; 2024-03-02: In Progress; 2024-03-03: In Progress; 2024-03-04: In Progress; 2024-03-05: In Progress; 2024-03-06: In Progress; 2024-03-07: In Progress; 2024-03-08: In Progress; 2024-03-09: In Progress; 2024-03-10: In Progress; 2024-03-11: In Progress; 2024-03-12: In Progress; 2024-03-13: In Progress; 2024-03-14: In Progress; 2024-03-15: In Progress; 2024-03-16: In Progress; 2024-03-17: In Progress; 2024-03-18: In Progress; 2024-03-19: In Progress; 2024-03-20: In Progress; 2024-03-21: In Progress; 2024-03-22: In Progress; 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress