## PROJECT PLAN
WORK PLAN (PROJECT PLAN) Objective: Complete Week 3 activities, tests and milestones before respective deadlines | time axis 2024-03-23 to 2024-06-05
Category | Action item/Deliverables | Owner | Resources | Start Date | End Date | Status
Milestone | Submit Milestone 3 | Me | Savanna | 2024-03-24 | 2024-03-30 | In Progress | 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress
Milestones | Catch up on all missing milestones | Me | Laptop | 2024-03-24 | 2024-03-30 | In Progress | 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress
Spaces | Identify my city hub | Me | Time | 2024-03-24 | 2024-03-25 | Done | 2024-03-24: Done; 2024-03-25: Done
Session | Attend Weekly support Session | Me | Laptop | 2024-03-27 | 2024-03-28 | Done | 2024-03-27: Done; 2024-03-28: Done
Portal Update | Update Employment Status on Portal | Me | Portal | 2024-03-28 | 2024-03-28 | Done | 2024-03-28: Done
VacAi | Work with Team memebers for relaunching of Vacai | Me | Laptop | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress
Daily | Prepare ToDolist for Next Week | Me | Laptop | 2024-03-29 | 2024-03-29 | In Progress | 2024-03-29: In Progress
Session#2 | Help Peers Who fall behind the Milestone Deadline | Me | Laptop | 2024-03-01 | 2024-04-15 | In Progress | 2024-03-23: In Progress; 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress; 2024-03-31: In Progress; 2024-04-01: In Progress; 2024-04-02: In Progress; 2024-04-03: In Progress; 2024-04-04: In Progress; 2024-04-05: In Progress; 2024-04-06: In Progress; 2024-04-07: In Progress; 2024-04-08: In Progress; 2024-04-09: In Progress; 2024-04-10: In Progress; 2024-04-11: In Progress; 2024-04-12: In Progress; 2024-04-13: In Progress; 2024-04-14: In Progress; 2024-04-15: In Progress
This Worksheet is last Updated on 29/03/2024

## ChatGPT Project Board
| Project Board Objective: Provide Update On VacAI | [6 empty] | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14
Task Name | Problem Stage | Assigned To | Priority | Resources | Start Date | End Date | Status
Submit Milestone 3 | 1. Discover | Me | High | Project documents, Previous milestones | 2024-03-24 | 2024-03-30 | In Progress | 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress
Catch up on all missing milestones | 2. Define | Me | High | Project documents, Milestone guidelines | 2024-03-24 | 2024-03-30 | In Progress | 2024-03-24: In Progress; 2024-03-25: In Progress; 2024-03-26: In Progress; 2024-03-27: In Progress; 2024-03-28: In Progress; 2024-03-29: In Progress; 2024-03-30: In Progress
Identify my city hub | 5. Launch | Me | Medium | Location maps, Local community resources | 2024-03-24 | 2024-03-25 | Done | 2024-03-24: Done; 2024-03-25: Done
Attend Weekly support Session | 1. Discover | Me | High | Calendar, Meeting link | 2024-03-27 | 2024-03-28 | Done | 2024-03-27: Done; 2024-03-28: Done
Work with Team memebers for relaunching of Vacai | 3. Design | Me | High | Calendar, Meeting link, Laptop | 2024-04-15 | 2024-04-15 | In Progress
Update Employment Status on Portal | 1. Discover | Me | High | HR portal access, Relevant information | 2024-03-28 | 2024-03-28 | Done | 2024-03-28: Done
Prepare ToDolist for Next Week | 1. Discover | Me | High | Task management tool | 2024-03-29 | 2024-03-29 | Done | 2024-03-29: Done
Help Peers Who fall behind the Milestone Deadline | 5. Launch | Me | High | Communication channels, Project documents | 2024-03-01 | 2024-04-15 | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress | In Progress
This Worksheet is last Updated on 29/03/2024